PA-508 Scranton/Lackawanna County Continuum of Care
PA-508 CONTINUUM OF CARE
FY 2026 Local Competition Public Timeline
	Dates may be adjusted if HUD issues additional guidance. Updates will be posted publicly and distributed to applicants.

	DATE
	ACTIVITY

	July 14, 2026
	Competition opens and materials are published.

	July 16, 2026
	PA-508 CoC Board meeting and ratification of revised materials.

	July 17, 2026
	Board-approved clarifications or amendments posted, if needed.

	July 21, 2026 - 10:00 a.m. ET
	Public meeting and applicant information session.

	July 24, 2026
	Deadline for written applicant questions.

	July 27, 2026
	Final FAQ posted.

	July 31, 2026 - 11:59 p.m. ET
	Local applications due.

	August 1-3, 2026
	Completeness and threshold review.

	August 4-6, 2026
	Independent review and scoring.

	August 7, 2026
	Preliminary decisions issued.

	August 9, 2026 - 5:00 p.m. ET
	Reconsideration deadline.

	August 10, 2026
	Final written notices and rankings issued outside e-snaps.

	August 11-17, 2026
	Selected applicants complete or revise e-snaps applications.

	August 18-21, 2026
	Technical, eligibility, and budget review.

	August 21, 2026
	Final supporting materials due.

	August 24, 2026
	CoC Consolidated Application and Project Priority Listing posted publicly.

	August 24-25, 2026
	Final review and submission preparation.

	August 26, 2026 - 8:00 p.m. ET
	HUD submission deadline.


Applicant Questions
Alex Lester | United Neighborhood Centers of Northeastern Pennsylvania | alester@uncnepa.org
FY 2026 Local Competition
